## Slide 1: City of Greater Dandenong Procurement Training
Unit 3: Contract Management
March 2025

## Slide 2: About ArcBlue
ArcBlue is a leading specialist procurement consultancy operating across Asia Pacific.
Our mission is to deliver positive change through procurement.
We support organisations to use procurement as a platform to achieve more – more savings, more efficiency, more insight, more social and sustainable outcomes, more value, more clarity, more influence, more flexibility, more assurance or more visibility.
Broad experience delivering products and programs in hundreds of organisations
Across 8 countries
In over 20 industries
Worked with numerous public and private sector companies
Local government to multi- national corporations
We have over 70 consultants as well as a pool of specialist project contractors.
Our team’s expertise spans all aspects of procurement and each of our consultants and contractors has practical internal procurement experience.

## Slide 3: Housekeeping
Time &
Schedule
Technical
Issues
Mute
Button
Participation
Questions
Digital
Academy
Notes: Session duration & breaks: Our MicroLearning session today will be x hours in durations. We will have a short 5-minute break around halfway. Please be punctual and adhere to break times specified.
Maintaining focus: Maintaining focus can be a challenge, especially when you’re learning remotely. We’ve included content and activities to keep engagement levels up, and it is expected that all participants take part in these activities.
Mute function: Please ensure you are muted when not speaking. The Zoom mute button is generally found in the bottom, left area of your screen. Sometimes you need to hover your mouse there for it to appear.
Questions:
(<12 participants) – Please feel free to speak up if you have questions throughout the presentation, by unmuting yourself. Remember that webinars are shorter than a standard training session so there may be times we need to park a question or topic.
(>12 participants) – Please utilise the Forum (chat function) within the Digital Academy for any questions you may have along the way. I will check them intermittently and answer them as soon as possible.
Technical issues: If you experience technical issues, please first check the Forum to see if others are experiencing the same problem, and alert me directly if there is a general problem. However, please do not interrupt the group / facilitator if the problem might be limited to just you. Should technical problems persist, please know that we will be recording the content and making it available after the session, within the Digital Academy.
Participation: Use teams/zoom functionality to participate, example the raise / chat function for questions.
Note for facilitators – things to be cautious of
Try to keep people on point when they’re asking questions. With only 2 hours, you’ll need to be cautious of questions that are actually statements or someone dominating the time.
Forum use: Be wary of people using the forum as a personal catch up session. It will be hard to keep everyone focused on as they’re working remotely.

## Slide 4
Contract Management Principles
Contract Management Enablers
Summary and Review
OHS Acts, Regulations and Guidance
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Phase 3: Contract Closure

## Slide 5: Introductions
Your
ROLE
Your
OBJECTIVES
KEY
CHALLENGES
you face

## Slide 6
Learning objectives
Contract Management Principles
Contract Management Enablers
Summary and Review
To acquire a high level understanding of concepts and principles essential for a Contract Manager
OHS Acts, Regulations and Guidance
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Phase 3: Contract Closure

## Slide 7: Definition: Contract Management
The process that ensures both parties to a contract fully meet their respective obligations to deliver both the business and operational objectives required from the contract.

## Slide 8: Why is Contract Management important?
1. Principles
To establish the contract and drive compliance
To ensure all parties understand and comply with their obligations
To ensure the goods/services are received to the agreed standard/performance at the agreed time and at the agreed cost
To realise, capture and track the anticipated benefits and value for money
To identify and manage in-contract risks
To transact as efficiently and effectively as possible
To identify continuous improvement opportunities and promote innovation
To manage the potential threat of scope creep
To manage the supplier relationship and reduce the chance of disputes
To manage any rights with respect to warranties etc.

## Slide 9: From a Contract Manager to a Good Contract Manager
A good contract manager ensure effective management of suppliers and downstream processes so the maximum potential value of a contract is obtained
Sourcing
Contract Management
Well managed, performing well
Adequate management, but performance drifting
Under-managed and under-performing
Time
Value
Value identified by sourcing
  In the absence of CM; sourcing identified value will fade over time
Manage and sustain long-term improvements to the category value chain
Unlock full-potential results by integrating Contract Management and Supplier Management
Realize and sustain sourcing value
Improve supplier relationships and accountability with Strategic and Preferred suppliers
Enhance business relationships; coordination with stakeholder goals
Proactive mitigation of enterprise risk (e.g. supply, sustainability, reputation, legal)
Drive efficient and effective procurement processes (e.g. S2P, contract compliance, PO cycle time)
Notes: Look at what you can achieve in a day in the life of a contract manager!

## Slide 10: Discussion
What goes wrong with contracts; what issues have you seen arise for contract managers?
Identify the kinds of contract problems you have encountered or heard about.

## Slide 11
Why do contracts go wrong?
Vague and confusing terminology
Inadequate specification
Inability to monitor and accept changes
Differing laws and conventions between the parties
Lack of continuity with key players and stakeholders
Role ambiguity
Fail to meet business needs
Incentivizes wrong behaviors
Incompatible relationship
Lack of understanding of contract
1. Principles
Unrealistic expectations
Notes: Unrealistic expectation means contract managers are not realistic about what can actually be delivered – quality, timelines, within KPIs

## Slide 12: How does the Contract Management Model fit in the Procurement Lifecycle?
Contract Management (CM) is a sub-process of the broader procurement lifecycle that from oversight of a procurement process with a supplier to adherence to agreed obligations, terms and conditions and eventually closure and termination
Contract Management (CM) Model has three phases:
  Phase 1 : Mobilise the Contract
  Phase 2 : Contract Management and Administration
  Phase 3 : Contract Closure
A comprehensive Occupational Health and Safety (OHS) management will serve as one of the key enablers to proficient CM as they will inform the requirements that drive not only the why, but the when, who, and how the enterprise mitigates risks (operational, reputational and legal damages)

## Slide 13
Learning objectives
Contract Management Principles
Contract Management Enablers
OHS Acts, Regulations and Guidance
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Summary and Review
Identify the key success factors in your organisation that support good practice contract management
Phase 3: Contract Closure

## Slide 14: Contract Management Enablers
Mandatory Induction and Training
Ensure roles and responsibilities are clearly understood;
Put appropriate resourcing in place (centrally and in business units)
Develop skills and expertise
Allocate personnel and time;
Include responsibilities in PDs and in staff performance management
Establish oversight clear assignment
Recognise good practice as a priority
Integrate and align practice with Procurement Policies and Guidelines
Model accountability for good practice
Contract Management Framework
Templates
Plans
Checklists
KPI Development Tools
Risk Management Framework
Framework and systems
Leadership and Culture
People
Notes: Leadership and Culture
Oversight has been established and clearly assigned
Good practice is widely recognised as a priority
Practice is integrated and aligned with Procurement Policies and Guidelines
accountability for good practice
People
A mandatory Induction and Training
Roles and responsibilities are clearly understood;
Appropriate resourcing is in place (centrally and in business units)
  Skills and Expertise
  Personnel and time;
Responsibilities are included in PDs and in staff performance management
Framework & Systems
Clear organisational framework
Good guidance and procedures
Sound records management processes
A contract register
Systems for recording all agreed contract information, including key ‘trigger points

## Slide 15
Learning objectives
Contract Management Principles
Contract Management Enablers
OHS Acts, Regulations and Guidance
Phase 3: Contract Closure
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Summary and Review
Current OHS landscape and where to source for guidance

## Slide 16: Discussion
Probity
What is Probity? What synonyms would you use?
Why is it relevant in Contract Management?

## Slide 17: Task 1
A variation request has come through from an incumbent supplier for $925,000 for additional works that are in addition to the original contract scope.
Even though the contract stipulates rates for variations based on hourly/daily rates, your manager wants to check whether this is a fair and competitive quotation so asks you to take the scope of additional services and float them out on the open market so that this price can be “benchmarked”.
Several suppliers provide quotations accordingly.
The lowest quote is then used to “lean on” the incumbent supplier to lower their price. The supplier that provided the lowest quote is not awarded the work (and there was never any intention to award to another supplier). The approach to the market was only for “benchmarking”.
What is questionable about this practice in terms of probity?

## Slide 18: Probity in Contract Management Practice
Supplier Selection
Evaluating submissions
Avoiding conflicts of Interest
Contract Management
Managing variations
Preventing fraud & misappropriation
Not accepting gifts & hospitality
Avoiding nepotism
Creating incentives
Managing conflicts of interest
Negotiating contracts
Minimise conflicts of interest
Ensure fairness and impartiality
Maintain confidentiality
Open and transparent activity
What is probity?
Where is probity important?

## Slide 19: The importance of OHS as a Contract Manager
      Review
      Review and document OHS Incidents and Remedial Actions
      Ensure OHS Management Systems are well recorded before contract closure
      Measure
      Review OHS Management Systems/Safe Work Method Statement Records
      Monitor Contractor OHS Performance
      Conduct Site Inspections
        Check PPE requirements
        Check COC/SWMS
      Manage Non-Conformances
      Plan
      OHS Risk Register/Classification
      Hazard ID Control Plan
      Hygienist Report
      Specification Development
        Scope inclusion of OHS Management Services
        Set Evaluation Criteria
Organise
      Ensure site inductions are conducted and recorded
      Ensure Monthly OHS Toolbox meetings are held
      Identification of High Risk Construction Work (HRCW) that require Safe Work Method Statements SWMS
OHS management is a contractor-managed process that a Contract Manager must monitor consistently
Procurement Manager
Project
Manager
Contract Manager

## Slide 20: OHS Acts, Regulations and Guidance
A good OHS Management Plan is the foundation of best practice OHS risk management and mitigation.
“Prevention is better than cure”
OHS Overview
OH&S management practice for staff has progressed significantly
OH&S obligations and practice for employers in relation to contractors are not as widely understood or recognised
The continued trend towards outsourcing has considerably increased the use of Contractors in industry and the need for effective management systems
Council’s contract complexity creates specific challenges for OH&S Management
  Small to large contractors
  Range of service areas and types of hazards
  Thin spread of Contract Managers

## Slide 21: OHS Acts and Regulations
Occupational Health and Safety Act 2004
The Occupational Health and Safety Act 2004 sets out the key principles, duties and rights in relation to occupational health and safety.
  The general nature of the duties imposed by the Act means that they cover a very wide variety of circumstances, do not readily date and provide considerable flexibility for a duty holder to determine what needs to be done to comply.
Occupational Health and Safety Regulations 2017
The Occupational Health and Safety Regulations 2017 (OHS Regulations) builds on the OHS Act. They set out how to fulfil duties and obligations, and particular processes that support the OHS Act. For example, they include requirements for:
  safe operation of major hazard facilities and mines
  training for high risk work
  managing and removing asbestos
  licences for specific activities
WorkSafe Victoria provides advice and guidance about what constitutes compliance with the Act and Regulations

## Slide 22: Important Contract Management Issues –Managing OHS Risk and Mitigation
Employer Duty of Care
The employer has the same duty of care for Contractors as they do for employees. Conversely, the Contractor owes a duty of care to the organisation, and its employees, to conduct its business in a safe manner.
Consequently the Principal or the Workplace Manager needs to make sure that:
  The Contractor is able to undertake the work in a competent and safe manner;
  Contractors & Sub-contractors are licensed (where required);
  Contractors have public liability and workers compensation insurance;
  Safe work procedures are sighted and reviewed;
  Prior to working on site, Contractors are appropriately inducted (Contractor Induction Checklist); and
  A role has been assigned and inspection regime established to monitor the compliance of contractors to OH&S standards.

## Slide 23
Learning objectives
Contract Management Principles
Contract Management Enablers
OHS Acts, Regulations and Guidance
Phase 3: Contract Closure
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Summary and Review
Become aware of the initial tasks to be performed to set up the contract and to initiate a contract to provide the best chance of success

## Slide 24: Contract Mobilisation
Contract mobilisation includes those key initial contract execution and transition steps, that begin with the awarding of the contract to the successful provider.
OHS
SYSTEMS
PROCESSES
COMMUNICATION
CONTRACT SIGNED?
PRICING
MITIGATE RISKS
COMMERCIAL
OPERATIONAL
TRANSITION
MILESTONES
SYSTEMS
RELATIONSHIP
RESPONSIBILITIES
ROLES
FRAMEWORK
MAPPING
USERS
IDENTIFICATION
COMMUNICATION
CHANGE MANAGEMENT
2. Mobilising Contracts
Variation and claims
Notes: Consider the Contract Management Process.
What is the primary focus for a Contract Manager at the mobilisation of a new contract?
Relationship
Users
OHS
Commercials
Operational
How does this focus inform your overall contract management approach and initial steps?

## Slide 25: Early Actions
Read the contract
Distribute and interpret the contract
Establish agreed post-contract management governance and processes
Validate baseline service scope, costs, levels and responsibilities
Managing additional requests beyond baseline
Foster realistic expectations of supplier performance
Measure and react to performance delivery as agreed
Promote the relationship
2. Mobilising Contracts

## Slide 26: Governance Structure- Assigning roles and responsibilities
2. Mobilising Contracts
KEY | R = Responsible | A = Accountable | C = Consulted | I = Informed
A formal governance structure will support decision, align disparate stakeholder groups to business objectives and engage on priority supplier escalated issues
Task | Roles |  |  | 
 | R | A | C | I
Set up kick off meeting |  |  |  | 
Receive, check and file insurance certificates and financial guarantees |  |  |  | 
Establish Contract objectives and key performance indicators |  |  |  | 
Review and approve Contractor OH&S plan |  |  |  | 
Set up financial tracking and controls |  |  |  | 
Conduct site inductions for Contractor staff |  |  |  | 
Set up and manage performance reviews |  |  |  | 
Assess KPIs and Contractor Performance |  |  |  | 
Authorise any variations during the Contract |  |  |  | 

## Slide 27: Task 2
Contract Risks
Identify and describe 3 key contract risks for a contract you know well.
Assess Likelihood and Impact and identify potential mitigating actions and responsible parties.
Prepare to feedback your responses to the rest of the group.

## Slide 28: Task – Contract Risks
POTENTIAL RISKS & MITIGATION PLAN (Probity, limited competition, etc.) |  |  |  | 
Risk Description | Likelihood (L/M/H/C) | Impact (L/M/H/C) | Mitigating Actions | Responsibility
KEY | L = Low | M = Medium | H = High | C = Critical

## Slide 29: Contract Risks - Examples
Lack of sufficiently skilled and experienced resources to effectively manage the contract(s)
Lack of recognition of the importance of contract management
Failure to act on Supplier under-performance
Supplier unable to deliver due to financial collapse or loss of resources
Fraud and/or unethical conduct by the Supplier
OHS or public liability issues
Unauthorized loss of data or breach due to ineffective security systems or poor employee compliance
Failure to provide contract deliverables on time, to agreed quality standards
Failure to adhere to agreed budget
Supplier failure to comply with jurisdictional laws and regulations as assumed steward of company
Human, wildlife, or natural environment impacts due to accidental or improper dispersal of effluents, emissions, wastes, etc…
Company’s inability to transition away from an undesirable or entrenched supplier relationships
Capability
Financial
OHS
Security
Supplier Performance
Regulatory
Sustainability
Exit strategy
Notes: Discussion on what can go wrong with a contract

## Slide 30: Contract segmentation by value and complexity/risk helps to focus contract management efforts
 | Description
Routine | These contracts are low value and low risk, usually transactional in nature. A ‘light touch’ approach is recommended (i.e. quite ‘hands off’ and doing the minimum).
Leverage | These contracts are high value, but low risk. The priority for managing these contracts will be on how to leverage the value as much as possible (e.g. monitoring spend, containing leakage, ensuring rebates & volume discounts are applied, maximising value added services that suppliers can offer).
Focused | These contracts are higher risk than routine contracts, but not high value. The priority for managing these contracts will be to focus on contract management activities that help minimise risk (e.g. closely monitoring performance against KPIs, regular reporting and meetings with the supplier etc. to pro-actively address any issues about performance).
Strategic | These contracts are high value and high risk to the organisation. These contracts require the most amount of rigour and attention to manage the contract and experiences contract managers.
Designs the contract management approach around the value and risk to your organisation
Scales the contract management tools, governance, time and effort in line with the complexity and value of that contract
overall_1_131910454158952321 columns_6_131913077477008606 10_0_131910454145300192 11_0_131910454147068323 13_1_131910454149745966 14_0_131910454150536534 15_0_131910454151497179 12_0_131913086036049457 27_1_132276712248614422 29_0_132278467348909295
Note: *Also referred to as the Kraljic Matrix
Value
Complexity
High
Low
Low
High
Strategic
(high value, high risk)
Routine
(low value, low risk)
Focused (low value, high risk)
Leverage
(high value, low risk)
Notes: Taking a ‘value risk’ approach simply means that there is flexibility in how you manage a contract based on its dollar value and risk to the organisation if the contract is not properly performed. This is a common sense approach, as there is no such thing as a ‘one size fits all’ when it comes to contract management.

## Slide 31: Contract Management Plan
  Operational management document for the contract, supporting the written contract
  Agreed and formalised following contract negotiation
  A living document that continues to be updated throughout the life of the contract (CM Register)
  Signed off by internal stakeholders
  May be signed off jointly with suppliers
  Critical part of the transition from Mobilise to the Manage phase
2. Mobilising Contracts

## Slide 32: Contract Management Plan - Sample Structure
Reference Information
Contract Management Approach
Background (Objectives, Scope & Key Deliverables)
Key Parties (supplier, stakeholders)
Key Milestones
Key documents (E.g. RACI Matrix and Transition Plan)
Conditions
Financial Considerations
Incentives and abatements
Other financial considerations
Performance Management & Contract Management processes
  KPIs and Reporting Requirements
  Transitions
  Conflicts and Disputes resolution
  Contract Variation Handling
Risk & Issue Management
  Risk management plan and Issue register
Process Improvement
  Post implementation review and Lessons learnt review
Notes: 12:30

## Slide 33: Kick-Off meeting
Kick off meetings are a key chance to ‘set the tone’ for the relationship and establish good working practices.
Objectives
  Transition from planning to execution and begin the process of delivering the Contract objectives
  Meet the Suppliers team and capture their plans to fulfil contract requirements in terms of performing to specifications and in compliance with service requirements
  Receive such certificates, assurances and documentary evidence as may be required to prove compliance with operating policies
  Begin joint planning and target setting and enabling success
  Begin developing a relationship with the Supplier and establishing rapport with their people
  It is essential that an Agenda is produced and detailed Minutes are recorded and agreed by both parties.
2. Mobilising Contracts

## Slide 34: Task 3
Contract Kick-off Meeting
You are starting a new contract with a new supplier. A kick-off meeting has been arranged for tomorrow. This is your first and best opportunity to set the tone for the contract.
How do you want the supplier to view your management style?
What tone do you think you might set?
What kind of meeting management might help to set the tone?

## Slide 35: Setting the tone
The Contract Kick-off Meeting can assist the contract manager to set the tone for how the contract is going to be managed. Ideas for the tone you might set include:
I am approachable, constructive and easy to do business with
I know my contract well, and will hold us all to account
I am assertive and will raise issues directly with you when required
I will monitor progress to check that we are getting what we are paying for
I expect all communications to come through me
I will manage changes, and will not be entertaining unnecessary variations
I expect innovative thinking and solutions
I will be pursuing all the incentives built into the contract
I will provide you with feedback, positive and negative
Notes: The kick off meeting is an opportunity to create an impression with you supplier about how you are going to manage the contract.

## Slide 36
Learning objectives
Contract Management Principles
Contract Management Enablers
OHS Acts, Regulations and Guidance
Phase 3: Contract Closure
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Summary and Review
To understand the key aspects of contract administration and performance management

## Slide 37: Contract Administration
Variations, claims and change control
Ordering
Monitoring costs
Monitoring and recording supplier performance (KPIs)
Payment and invoicing
Provision of management information/ reporting
Record keeping for the audit trail
3. Contract Administration
Handling the formal governance of the contract e.g. contract maintenance, change control, cost monitoring, payment, management reporting etc.
Notes: 37

## Slide 38: Contract Administration
3. Contract Administration
Features
Maintaining an updated contract file, including a hard, signed copy of the contract that is easily accessible when required and all on-going correspondence and contract information.
Using contract management software to record key information, supplier contact details and the scope of services to be provided.
Ensuring there is regular reporting of contract information, including payments, compliance levels, performance metrics and variations
Documents that may need to be created and retained
Copy of the contract signed by both parties
Risk assessments
Contract management plan or checklists
Records of payments
Records of performance
Variations to the contract
Assistance or expert external advice received

## Slide 39: Maintaining Records
It is important to keep detailed and accurate records:
They provide facts and valuable evidence in the event of a dispute or claim
They provide information on which price negotiations can be based
They highlight areas where the Contractor has under-performed
They provide an audit trail for financial, commercial, QA and safety issues
Controlling time and material working
A legislative requirement
Those dealing with the Contract should keep:
A daily diary/log recording all events of the day, progress, problems, resources, information, delays, discussions etc.
Photographs of progress, problems and incidents whenever possible which are invaluable in disputes
A chronological file of instructions, correspondence, meeting minutes, certificates, reports, waiting time notifications, day work sheets etc.
A master contract file - should be maintained and contain the master contract documentation plus any relevant correspondence
3. Contract Administration
All relevant files are to be stored in Objective

## Slide 40: Contract Performance Management Process
      Review Agenda, feedback, KPI’s, Claims, Variations, corrective actions, supplier data, performance trends, Process Improvement Plan
      Measure KPI’s, Hazard & housekeeping, Register of Claims & Variations, Work logs, Progress vs. Plan, Invoice/Payment summaries, Key Personnel Attendance Record, Register of Assets, Safety Record.
      Plan Gantt Chart, Milestones, Contract Management Plan, Project Definition Statement, Work Breakdown Structure, Asset, Communications Plan, Resource Plan, OHS Management Plan
Organise
      Organisation Chart, Contact List, Role & Responsibilities, RACI, Meeting Schedule – Agenda, correspondence file, Risk Management Schedule, Audit Plan
      Measure
      Review
      Plan
      Organise

## Slide 41: Discussion
Performance management
What is the purpose of performance management for contract managers?
What does performance management look like?

## Slide 42: Performance Measurement – Key Performance Indicators
4. Managing performance
Relevance | Is it relevant to the organization’s performance goals?
Validity | Does the measure actually measure what it is supposed to?
Attribution | Does it relate to factors that decision makers can affect?
Clarity | Is it understandable?
Accuracy | Does it provide correct information to accepted standards?
Comparability | Can the data be used to make comparisons?
Consistency | Does it relate to the same factors in all cases at all times?
Timeliness | Can data be collected & processed within a useful timeframe?
Cost | Is its value greater than the data collection costs?
A key performance indicator (KPI) is a measure to evaluate the
success of the supplier in meetings the objectives of the contract.
KPIs can be built into the contract.
However. if they are not the contract management will need to put appropriate KPIs in place.
Creating an effective KPI can be challenging.
Notes: 2:45pm
  E.g. Customer Satisfaction/Resolution times versus Response times
  Use suppliers’ experience in defining functional outcomes
  Detailed requirements for specific standards/regulatory requirements
  Targets
    There must be a benefit from the improvement
    Aim to ensure both sides benefit

## Slide 43: Contract Management – Types of KPIs
Type | What it is | Examples
Input | Measure of resources applied to a contract | # Headcount
Process | Measures efficiency of the contract | Call handling time
Output | Measures the results | Percentage savings
Leading | Measures current performance | % Market share
Lagging | Measures historical performance | Revenue
Qualitative | Measures based on subjectivity | Survey % answers ‘very good’
Quantitative | Metric based statistics | Delivery on time

## Slide 44: Leading and lagging indicators
Leading indicators:
Lagging indicators:
These are typically “output” oriented, easy to measure but hard to improve or influence
Example:
Fault responded to and cleared within 48 hours
Savings achieved by the program
These are typically input oriented, hard to measure and easy to influence
Examples:
Call acknowledged within 1-hour
First availability of support spares 98%
Team dispatched within 2-hours of receiving call
Status update given to customer team within 30 minutes of arrival on site
4. Managing performance
Notes: 3pm

## Slide 45: Example KPIs..
KPI | Example Leading KPI | Example Lagging KPI
OHS | Number of Management OHS Visits | TRIF = Frequency of total recordable injuries / 200,000 man hours
Efficiency | Attendance at planning meetings | % of jobs delivered according to agreed plan
Quality | Compliance with quality plan | % rework required
People | % performance appraisals completed | % turnover of personnel
Innovation | Number of innovative ideas submitted by supplier | Value added to the company from innovative ideas
Cost | Actual cost vs plan budget | $ savings achieved
4. Managing performance

## Slide 46: The KPI funnel
Increasing detail
What is the overall purpose of the relationship?
How does the supplier achieve this overall purpose?
What are the key activities to reach the objective?
How do we measure and report on the indicators?
What are the targets or indicators to reach the objectives?
Target setting
Notes: KPI’s must be aligned to your goals

## Slide 47: KPI’s should be…
S
Specific
Communicates the requirement clearly, concisely, logically and unambiguously.
M
Measurable
Contains enough information for tenderers to cost the goods or services they will offer.
A
ACHIEVABLE
Permits the offered goods or services to be evaluated against stated criteria or standards
R
T
Time-bound
What is a realistic timeframe?
4. Managing performance
RELEVANT
Fulfils the need, not over specifying or including “nice to haves”.
Notes: 2:30pm Break

## Slide 48: Task 4
In small groups, identify a contract that one of you is currently managing. Identify two critical actions of the supplier where a KPI would be beneficial.
Then build one SMART KPI that could be applied to this contract.
* Tip – Use the KPI funnel on slide 46 to help determine the key activities.

## Slide 49: KPIs - Checklist
  Is the supplier ultimately accountable? Are they responsible?
  Are there any outside factors that affect the performance of the objectives?
  Is data self-assessed by the supplier or can it be verified independently?
  Are the targets clear and jointly understood?
  Remember the type of supply relationship we want to develop
  Review KPIs regularly for relevance and if necessary, update
  If there are too many KPIs, if they are too difficult to measure, and if targets are not realistic, supply performance will be at risk.
  Ensure key link to Scope of Work or Specification
  Cannot make up for a poor Scope of Work or Specification
4. Managing performance
Notes: How do you measure/report on the activity? Does the supplier have systems?? Do you invent a process in the SoW to cover this eg: checksheets?

## Slide 50: Contract Management - Review
Agreed checkpoints for taking a reality check on the supplier and the contract. Contract review meetings should be held regularly (monthly/quarterly as required). All the relevant people from client and contractor should attend.
It is essential that an Agenda is produced and that detailed minutes are recorded and agreed by both parties.
Have a clear and agreed agenda:
      Invite the other party to contribute to reduce the possibility of surprises
      Ensure clarity of objective and don’t lose sight of it
      Prepare and distribute any necessary materials
Be clear about who you want to meet with and why
Know what information you seek and what you are going to do with it
Be wary of the presentation that tells you only what they want to!
Prepare a summary of the meeting and assign any agreed actions
At a minimum, the meeting should cover:
Actions from previous meeting
Performance achieved
Progress: Planned/actual
Issues arising
Corrective actions required
4. Managing performance
Notes: Good contract review practices
  Hold a pre-meeting internally to review data
  Use a standard meeting agenda to ensure there are “no surprises” and that all issues get on the table
  Invite the right attendees on both sides of the table
  Keep the conversation at the right level
  Not all one-way conversation – allow space for supplier
  Clear agreement on actions
  Think about themes for the coming period
  Link the meetings together through action setting and tracking

## Slide 51: Running Review Meetings
Focus of the Performance Review Meeting
60% looking forward
40% looking back
Business opportunities
Continuous Improvement
New actions
Performance
Issues
Trends

## Slide 52: Example Review Meeting Agenda
Introductions
Company/Supplier update
  Organisational/corporate changes
  Changes to governance or key personnel
  Capacity performance
  Cost challenges
  Engineering challenges
Review of previous meeting’s minutes and action items.
Financial – review of payments, mismatches etc.
Review of last period’s performance and trends
  KPI review
  Current issues with supplier performance – action plans
  Key themes such as resource support, process improvement
  Responsiveness – e.g. quote support, Problem resolution etc….
  What can we do to improve performance?
Status of mutual improvement efforts
Risk and business continuity
Relationship – review and measurement
New business opportunities
  Open RFQ’s – If appropriate
  Bid status on closed RFQ’s – If appropriate
Set direction for next quarter

## Slide 53: Managing Contractor Disputes
Negotiation | Aims to reach a mutually acceptable solution. One party should not feel unduly pressured to agree to a particular solution as this can lead to an escalation or reappearance of the dispute.
Mediation | Uses a neutral third party to assist in resolving the dispute – faster & less formal
Arbitration | Obtain a final and enforceable result without the costs, delays and the formalities of litigation.
Litigation | Seeking redress through the courts – expensive, time consuming & last resort
Expert support and advice early – internal and external if needed
Understand your contract and your contract clauses
Determine and assess risks
Plan your approach
Document clearly at all stages
Choose the right approach:
Notes: 53

## Slide 54: Variations
What is a variation?
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 1 | 1 | 1
Changes in…
Notes: Changes in:
Scope (quantity, quality, service, specification)
Price (price adjustments in accordance with adjustment forumla in the contract are not variations)
Time (extensions of time allowed under the contract are not variations)

## Slide 55: Discussion
Why do variations arise?
Are variations good or bad?

## Slide 56: Causes of Variations
Causes of variations:
Requests for additional goods, services or works
Unexpected requirement for increase in quantities
Specification revisions and adjustments
Technology changes or improvements
Changes in legislation
Demand fluctuations
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 1 | 1 | 1
Pricing of new or changed requirements
Changes to rates due to input costs changes (e.g. fuel price increases)
Contract extensions
CGD change to schedule
Contract extensions
Notes: Requests for additional goods, services or works – quantity, nature of the goods/services/works
Unexpected requirement for increase in quantities (e.g. presence of unexpected rock in construction excavation)
Changes in legislation (e.g. industrial relations legislation)
Demand fluctuations (e.g. changes in consumer demand of service provided by an outsourced service provider)
Contract extensions are treated as variations under the CGD Procurement Policy.

## Slide 57: CGD Policy on Variations
The CGD Procurement Policy deals with variations in price as follows:
“Where a variation occurs, the delegation is not defined by the value of the variation, but by the value of the whole contract.
An officer with a sub-delegation from the Chief Executive Officer or Council may vary a contract to the limit in the Instrument of Sub-Delegation.
Approved budget must be available for all variations.”
Value of whole contract = Original approved contract value
+
Cumulative value of all previous variations
+
Value of the current variation

## Slide 58: Effects of Variations
3. Contract Administration
Direct effects | Indirect effects
Increased cost of contract Possibly putting the contract over budget Requests for additional funds Extensions of time | Wasted and/or additional design work Supply chain effects New orders placed by the contractor Time/delay consequences - re-programming of the contract Unproductive costs Consequential costs such as impact on other contractors/activities Additional head office time and money

## Slide 59: Managing Variations
3. Contract Administration
  Require early warning of potential claims
  Use a ‘change control’ procedure which:
  Ensures all changes are appropriately authorised
  Records at least financial, time and quality impacts of the work covered by the variation along with the cumulative impact on the contract as a whole
  Treat as getting a new contract
  Obtain a firm quotation
  Challenge the quoted price
  Look for a reduction in price
  Agree the full implication
  Keep all parties informed
  Keep full record in contract log
  Oral variations only in emergency……and confirm in writing

## Slide 60
Learning objectives
Contract Management Principles
Contract Management Enablers
OHS Acts, Regulations and Guidance
Phase 3: Contract Closure
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Summary and Review
To understand the activities supporting an effective and risk-managed transition out of a contract

## Slide 61: Managing the Exit of a Supplier
The process is the same regardless of the reason for exit
The exit/termination process should form part of the original agreement
Provide notice of exit or termination
Define and agree clear milestones to ensure handover of data and return of assets
Agree responsibilities on both sides
Use financial levers or incentives if appropriate
4. Managing performance
Notes: 3:40pm

## Slide 62: Final Performance Review
Performance
Variations, Claims and Disputes
Lessons Learned
Contract objectives achieved?
Supplier performance measured (KPIs, budget, schedule)
Management performance (supplier and buyer)
User satisfaction (customer)
Contract variations
Disputes
Outstanding commercial/financial issues
Liquidated damages
What went well
What went less well
Where can improvements be made
Audit reports and findings

## Slide 63: Close out meeting
The close-out meeting should be held at the end of the contract. All the relevant people from client and contractor should attend.
The meeting should cover:
  Contractor delivery performance achieved
  Financial Performance
  Health & Safety and Environmental Performance.
  Management Performance (both contractor and client organisation)
  Documentation – Agreement on dates for receipt.
  Outstanding commercial / financial issues.
  Liquidated Damages
  Recording of lessons learnt and feedback into both organisations.
It is essential that an Agenda is produced and that detailed minutes are recorded and agreed by both parties.
4. Managing performance

## Slide 64
Learning objectives
Contract Management Principles
Contract Management Enablers
OHS Acts, Regulations and Guidance
Phase 3: Contract Closure
Phase 2: Contract Administration and Management
Phase 1: Mobilise Contracts
Summary and Review
To summarise learnings, become aware of further resources and assistance available and to close out the learning contract

## Slide 65: Key tools and controls throughout the contract management process
WHEN THINGS
HAVE GONE WRONG
Liquidated Damages
Parent Company
Guarantee
Dispute Resolution
Termination
The Law
Contract
Mobilisation
Contract
Administration
Contract
Management
START
DURING
END
Contract Closure
Final Performance
Review
What is Contract Management?
Contract Management
Enablers
OHS Act, Regulations
and Guidance
4. Managing performance
Notes: 4pm

## Slide 66: Feedback
We value your feedback – please take 5 minutes to fill in the online Training Feedback Survey

## Slide 67
Advisory & Change
Capability Development
Sustainable & Social Procurement
Project Contracting
Search & Recruitment
Procurement Technology
+61 (03) 8400 4220
info@arcblue.com.au
arcblue.com